## Sheet1 (hidden)
BUSTAP
ALCARAZ, ANGOT, BESMANO, BRIOSO
GANTT CHART
Tasks | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
| 2018-01-31 | 2018-02-07 | 2018-02-14 | 2018-02-21 | 2018-02-28 | 2018-03-07 | 2018-03-14 | 2018-03-21 | 2018-03-28 | 2018-04-04 | 2018-04-11 | 2018-04-18 | 2018-04-26 | aaa
Project Charter Document | bar: Week 1
Scope of work Document | bar: Week 2
Work breakdown structure | bar: Week 3
Gantt chart | bar: Week 3
Software requirment specifications | bar: Week 3
Software Development | bar: Week 2 to Week 12
Testing and Assurance Test | bar: Week 12
Finalize Documentation | bar: Week 12 to Week 13

## Sheet2
Name | Duration | Start |  | Finish |  | Resource Name
PLANNING
Meeting | 4 Months | 2018-01-31 | 8:00 | 2018-04-25 | 11:30 | Project Manager: | Annalyn Alcaraz
Analysis
Gathering of Requirements | 4 Months | 2018-01-31 | 8:00 | 2018-04-25 | 11:30
Software Development | [5 empty] | Developers: | Sammy Angot
Login + Menu | 30 days | [5 empty] | Justin Besmano
Locate Bus Stop | 30 days | [5 empty] | Job Brioso
Map Feature | 30 days
Reservation | 30 days
User Satisfaction | 30 days
Other Feature | 30 days
Documentation
Vision Document | 7 days | 2018-01-31 | 8:00 | 2018-01-31 | 23:00 | Justin Besmano
Scope of work Document | 7 days | 2018-01-31 | 8:00 | 2018-02-07 | 7:00 | Sammy Angot
Work Breakdown Structure | 5 days | 2018-02-07 | 8:00 | 2018-02-12 |  | Sammy Angot
SRS | 7 days | 2018-02-07 | 8:00 | 2018-02-14 |  | Justin Besmano
Other Document | 7 days
Testing and Assurance
Deployment | 14 days | 2018-04-18 |  | 2018-04-26
Finalize Documentation
Finalize Documentation | 7 days | 2018-04-18 |  | 2018-04-26

## FINAL_WBS
NAME |  | DURATION | DURATION | START | FINISH | RESOURCE NAME
1 | PROJECT PLANNING |  | 79 Days | 06/21/16 | 2017-08-09
1.1 | Planning |  | 21 Days | 06/21/17 | 07/18/17
1.1.1 | Identify Group Members |  | 3 Days | 06/21/17 | 06/23/17 | Project Manager: | Annalyn Alcaraz
1.1.2 | Identify Problem Domain |  | 7 Days | 06/26/17 | 2017-04-07
1.1.3 | Prepare Project Plan |  | 6 Days | 2017-04-07 | 2017-11-07 | Developers: | Sammy Angot
1.1.4 | Update Project Plan |  | 5 Days | 2017-12-07 | 07/18/17 |  | Justin Besmano
1.2 | Research |  | 25 Days | 2017-03-08 | 08/18/2017 |  | Job Brioso
1.2.1 | Interview |  | 5 Days | 2017-03-08 | 2017-09-08
1.2.2 | Surveys |  | 15 Days | 07/24/17 | 2017-11-08
1.2.3 | Finalize Survey + Interview Results |  | 5 Days | 08/14/17 | 08/18/17
1.3 | Documentation |  | 33 Days | 06/21/17 | 2017-08-09 | Annalyn Alcaraz
1.3.1 | Weekly Status Report |  | 13 Days(1 Report per week) | 06/21/17 | 2017-06-09 | Sammy Angot
1.3.2 | Finalize Project Proposal |  | 15 Days | 08/14/17 | 2017-01-09 | Justin Besmano
1.3.3 | Milestone: Project Proposal Approval |  | 5 Days | 2017-04-09 | 2017-08-09 | Job Brioso
2 | ANALYSIS |  | 75 Days | 09/25/17 | 2018-09-01
2.1 | Revise Project Documentation |  | 20 Days | 09/25/17 | 2017-06-10
2.1.1 | Finalize Revisions |  | 10 Days | 09/25/17 | 2017-06-10
2.1.2 | Started Drafting other documents (Vision and scope, SRS, etc.) |  | 10 Days | 2017-02-10 | 10/13/2017
2.2 | Project Design |  | 55 Days | 2017-09-10 | 2017-09-01 | Annalyn Alcaraz
2.2.1 | Create System Diagrams |  | 40 Days | 2017-09-10 | 2017-01-12 | Sammy Angot
2.2.2 | Review + Present Diagrams |  | 10 Days | 2017-11-12 | 12/22/17 | Justin Besmano
2.2.3 | Update Diagarms |  | 5 Days | 2018-03-01 | 2017-09-01 | Job Brioso
3 | PROJECT DEVELOPMENT |  | 50 Days | 02/18/2017 | 2018-04-03
3.1 | Develop Passenger System |  | 50 Days | 02/18/2018 | 2018-04-04
3.1.1 | Develop Login + Menu |  | 5 Days | 01/18/2018 | 01/24/2018 | Justin Besmano
3.1.2 | Develop Locate Bus + Bus Stop Feature Develop Locate Bus + Bus Stop Feature Login + Menu |  | 10 Days | 01/25/2018 | 2018-07-02 | Job Brioso
3.1.3 | Map Feature |  | 5 Days | 2018-08-02 | 02/14/2018
3.1.4 | Reservation System |  | 20 Days | 02/15/2018 | 03/14/2018
3.1.5 | Congestion Forecasts |  | 10 Days | 03/15/2018 | 03/28/2018
3.1.6 | User Review Module |  | 5 Days | 03/29/2018 | 2018-04-04
3.2 | Develop Back End |  | 35 Days | 2018-08-02 | 03/23/2018
3.2.1 | Develop Login + Menu for Administrator |  | 5 Days | 2018-08-02 | 02/14/2018 | Annalyn Alcaraz
3.2.2 | Develop storage for congestion status and News reports |  | 15 Days | 02/15/2018 | 2018-07-03 | Sammy Angot
3.2.3 | Develop other Feature + Front End |  | 15 Days | 2018-02-03 | 03/27/2018
4 | IMPLEMENTATION |  | 10 Days | 041/05/20187 | 04/19/2017
4.1 | Testing |  | 10 Days | 2018-05-04 | 04/19/2018
4.1.1 | Develop Test Report |  | 1 Day | 2018-05-04 | 2018-05-04
4.1.2 | Test System |  | 7 Days | 2018-09-04 | 04/17/2018 | Team | Annalyn Alcaraz
4.1.3 | Implement System |  | 2 Days | 04/18/2018 | 04/19/2018 |  | Sammy Angot
5 | CLOSURE |  | 6 Days | 04/29/2017 | 04/26/2017 |  | Justin Besmano
5.1 | Project Handoff |  | 6 Days | 04/29/2018 | 04/26/2018 | Team | Job Brioso
5.1.1 | Finalize Project Documentation |  | 3 Days | 04/19/2018 | 04/23/2018
5.1.2 | Complete Project Requirements |  | 2 Days | 04/23/2018 | 04/24/2018
5.1.3 | Assess group performance |  | 1 Days | 04/25/2018 | 04/25/2018