## WBS Diagram
WBS OUTLINE & DIAGRAM TEMPLATE
WBS OUTLINE & DIAGRAM TEMPLATE
PROJECT TITLE | COMPANY NAME
PROJECT MANAGER | DATE
CLICK HERE TO CREATE WBS OUTLINE & DIAGRAM TEMPLATES IN SMARTSHEET
BUS TAP: PASSENGER INFORMATION SYSTEM
PROJECT PLAN
1.1
Planning
1.2
Research
1.3 Documentation
1.1.1
Identify Group Members
1.1.2
Identify Problem Domain
1.1.3
Prepare
Project Plan
1.1.4
Update Project Plan
1.2.1 Conduct Surveys
1.2.2 Conduct Interviews
1.2.3
Study Business Market
1.3.1
Weekly Status Report
1.3.2
Finalize Project Proposal
1.3.3 Milestone: Project Proposal Approval
ANALYSIS
2.1
Gathering of Requirements
2.2
Project Design
2.1.1
Revise Project Documentation
2.1.2
Finalize Project Specifications
2.1.3
Do other formal documents (Vision and scope, SRS, etc.)
2.3.1
Create System Diagrams
2.3.2
Review Diagrams
2.3.3
Update Diagarms
PROJECT DEVELOPMENT
3.1
Develop Passenger System
3.2
Develop Back End
3.1.1
Develop
Login + Menu
3.1.2
Develop Locate Bus + Bus Stop Feature
3.1.3
Map Feature
3.1.4
Reservation System
3.1.5
Congestion Forecasts
3.1.6
User Review Module
3.2.1
Develop Web Application
3.2.2
Develop
Login + Menu for Administrator
3.2.3
Develop storage for congestion status and News reports
IMPLEMENTATION
4.1
Acceptance
4.2
Testing
4.1.1
Develop Test Report
4.1.2
Develop Acceptance Report
4.1.2
Develop Test Report
4.2.2
Test System
4.2.3
Configure Errors
CLOSURE
5.1
Project Handoff
5.2
FInalize DOcumentation
5.3
Group Assessment
5.1.1 Develop Installation Plan
5.1.2
Turn Over system
5.1.3
Install system at locations
5.1.3
Conduct Acceptance Test
5.2.1
Finalize Project Documentation
5.2.2
Complete Project Requirements
5.3.1
Assess group performance
5.3.2
Identify the good and bad remarks in the project
5.3.3
End the Project

## WBS Outline
WBS OUTLINE & DIAGRAM TEMPLATE
PROJECT TITLE |  | COMPANY
PROJECT MANAGER |  | DATE
PROJECT TITLE
1 | PROJECT PLAN
1.1 | Planning
1.1.1 | Identify Group Members
1.1.2 | Identify Problem Domain
1.1.3 | Prepare Project Plan
1.1.4 | Update Project Plan
1.2 | Research
1.2.1 | Conduct Surveys
1.2.2 | Conduct Interviews
1.2.3 | Study Business Market
1.3 | Documentation
1.3.1 | Weekly Status Report
1.3.2 | Finalize Project Proposal
1.3.3 | Milestone: Project Proposal Approval
2 | ANALYSIS
2.1 | Revise Project Documentation
2.1.1 | Finalize Project Specifications
2.1.2 | Do other formal documents (Vision and scope, SRS, etc.)
2.2 | Project Design
2.2.1 | Create System Diagrams
2.2.2 | Review Diagrams
2.2.3 | Update Diagarms
3 | PROJECT DEVELOPMENT
3.1 | Develop Passenger System
3.1.1 | Develop Login + Menu
3.1.2 | Develop Locate Bus + Bus Stop Feature Develop Locate Bus + Bus Stop Feature Login + Menu
3.1.3 | Map Feature
3.1.4 | Reservation System
3.1.5 | Congestion Forecasts
3.1.6 | User Review Module
3.2 | Develop Back End
3.2.1 | Develop Web Application
3.2.2 | Develop Login + Menu for Administrator
3.2.3 | Develop storage for congestion status and News reports
4 | IMPLEMENTATION
4.1 | Acceptance
4.1.1 | Develop Test Report
4.1.2 | Develop Acceptance Report
4.2 | Testing
4.2.1 | Develop Test Report
4.2.2 | Test System
4.2.3 | Test System
5 | CLOSURE
5.1 | Project Handoff
5.1.1 | Develop Installation Plan
5.1.2 | Turn Over system
5.1.3 | Install system at locations
5.1.4 | Conduct Acceptance Test
5.2 | Project Handoff
5.2.1 | Finalize Project Documentation
5.2.2 | Complete Project Requirements
5.1.3 | Install system at locations
5.2 | Project Handoff
5.3.1 | Assess group performance
5.3.2 | Identify the good and bad remarks in the project
5.3.3 | Identify the good and bad remarks in the project