## UUCP
USE CASE | TRANSACTION | WEIGHT | UUCP
LOGIN | 2 | 5 | 45
RESERVATION | 7 | 10
PLAN TRAVEL | 2 | 5
LOCATE BUS | 2 | 5
PROVIDE FEEDBACK | 4 | 5
CHECK BALANCE | 2 | 5
GENERATE BUS SCHEDULE | 1 | 5
GENERATE REPORTS | 1 | 5

## TCF
FACTOR | WEIGHT | RELEVANCE | PRODUCT
DISTRIBUTED SYSTEM | 2 | 5 | 10
RESPONSE OR THROUGH PUT ARE OBJECTIVES | 1 | 5 | 5
END-USE EFFICIENCY | 1 | 0 | 0
COMPLEX INTERNAL PROCESSING | 1 | 2 | 2
CODE MUST BE REUSABLE | 1 | 1 | 1
EASY TO INSTALL | 0.5 | 4 | 2
PORTABLE | 2 | 5 | 10
EASY TO CHANGE | 1 | 0 | 0
CONCURRENT | 1 | 0 | 0
HAS SPECIAL SECURITY FEATURE | 1 | 2 | 2
PROVIDES DIRECT ACCESS FOR 3RD PARTIES | 1 | 4 | 4
SPECIAL USER TRAINGIN FACILTIIES REQUIRED | 1 | 0 | 0
TOTAL TFACTOR for FirstPOS |  |  | 36
TCF = 0.6 + 0.01 * TFACTOR
0.96 | TCF

## ENVIRONMENTAL
FACTOR | WEIGHT | RATING
FAMILIAR WITH INTERNET PROCESS | 1.5 | 3
APPLICATION EXPERIENCE | 0.5 | 1
OBJECT-ORIENTED EXPERIENCE | 1 | 3
LEAD ANALYST CAPABILITY | 0.5 | 1
MOTIVATION | 1 | 3
STABLE REQUIREMENTS | 2 | 1
PART-TIME WORKERS | -1 | 0
DIFFICULT PROGRAMMING LANGUAGE | -1 | 0
TOTAL |  | 12
EFACTOR
EF = 1.4 - 0.03 * EF
1.04 | EF

## AUCP
UCP = UUCP * TCF * EF
44.928 | 45
900

## ESTIMATES
STAGES
STAFF | PLANNING | ANALYSIS | DEVELOPMENT | TESTING | IMPLEMENTING | TOTAL
| (16 weeks) | (15 weeks) | (10 weeks) | (2 weeks) | (1 week)
Project Manager | 30 hours * 16 weeks | 30 hours * 14 weeks | 30 hours * 12 weeks | 30 hours * 2 weeks | 30 hours * 1 week | 1290
Systems Analyst | 30 hours * 14 weeks | 30 hours * 14 weeks | 30 hours * 12 weeks | 30 hours * 2 weeks |  | 1260
Designer |  | 30 hours * 14 weeks | 30 hours * 12 weeks | 30 hours * 2 weeks |  | 840
Software Developer |  |  | 30 hours * 12 weeks | 30 hours * 2 weeks | 30 hours * 1 week | 450
Reviewer |  |  |  |  | 30 hours * 1 week | 30
| 840 | 1260 | 1440 | 240 | 135 | 3870
593
0

## Sheet1 (hidden)
182
360
38
13

## Estimate Updated
Tasks | Number of Days |  |  | Total Number of hours
PLANNING |  |  |  | 182
Identify Group Members | 3 Days | 2 hours * 3 Days |  | 6
Identify Problem Domain | 7 Days | 4 hours * 7 Days |  | 28
Prepare Project Plan | 6 Days | 2 hours * 6 Days |  | 12
Update Project Plan | 5 Days | 2 hours * 5 Days |  | 10
Interview | 5 Days | 4 hours * 5 Days |  | 20
Surveys | 15 Days | 2 hours * 15 Days |  | 30
Finalize Survey + Interview Results | 5 Days | 2 hours * 5 Days |  | 10
Weekly Status Report | 13 Days(1 Report per week) | 2 hours * 13 Days |  | 26
Finalize Project Proposal | 15 Days | 2 hours * 15 Days |  | 30
Milestone: Project Proposal Approval | 5 Days | 2 hours * 5 Days |  | 10
ANALYSIS |  |  |  | 230
Finalize Revisions | 10 Days | 2 hours * 10 Days |  | 20
Started Drafting other documents (Vision and scope, SRS, etc.) | 10 Days | 2 hours * 10 Days |  | 20
Create System Diagrams | 40 Days | 4 hours * 40 Days |  | 160
Review + Present Diagrams | 10 Days | 2 hours * 10 Days |  | 20
Update Diagarms | 5 Days | 4 hours * 5 Days |  | 10
Development |  |  |  | 360
Develop Login + Menu | 5 Days | 4 hours * 5 Days |  | 20
Develop Locate Bus + Bus Stop Feature Develop Locate Bus + Bus Stop Feature Login + Menu | 10 Days | 4 hours * 10 Days |  | 40
Map Feature | 5 Days | 4 hours * 5 Days |  | 20
Reservation System | 20 Days | 4 hours * 20 Days |  | 80
Congestion Forecasts | 10 Days | 4 hours * 10 Days |  | 40
User Review Module | 5 Days | 4 hours * 5 Days |  | 20
Develop Login + Menu for Administrator | 5 Days | 4 hours * 5 Days |  | 20
Develop storage for congestion status and News reports | 15 Days | 4 hours * 15 Days |  | 60
Develop other Feature + Front End | 15 Days | 4 hours * 15 Days |  | 60
Implementation |  |  |  | 38
Develop Test Report | 1 Day | 2 hours * 1 Day |  | 2
Test System | 7 Days | 4 hours * 7 Days |  | 28
Implement System | 2 Days | 4 hours * 2 Days |  | 8
Project Handoff |  |  |  | 13
Finalize Project Documentation | 3 Days | 2 hours * 3 Day |  | 6
Complete Project Requirements | 2 Days | 4 hours * 2 Days |  | 6
Assess group performance | 1 Days | 1 hour * 1 Day |  | 1
|  |  | Total Hours | 823