## Sheet1
Activity # | Activity Name | Activity Name Description | # of Days | Start Day | Dependency | Milestone
1 | Planning |  | 79 Days | 06/21/2017
1.1.1 | Identify Group Members | Initial Phase+C2:C21 | 3 Days | 06/21/2017
1.1.2 | Identify Problem Domain | Brainstorming | 7 Days | 06/26/2017
1.1.3 | Prepare Project Plan | Initial Project Proposal | 6 Days | 2017-04-07 | 1.1.2FS
1.1.4 | Update Project Plan | Revised Plan | 5 Days | 2017-12-07 | 1.1.3FS | Initial Project Plan
1.2.1 | Interview | Data Gathering | 5 Days | 2017-03-08
1.2.2 | Surveys | Data Gathering | 15 Days | 07/24/2017
1.2.3 | Finalize Survey + Interview Results | Compile Result Set | 5 Days | 08/14/2017 | 1.2.1 + 1.2.2 FS
1.3.1 | Weekly Status Report | Progress Report | 13 Days(1 Report per week) | 06/21/2017
1.3.2 | Finalize Project Proposal | Final Project Proposal | 15 Days | 08/14/2017 | 1.1.4 FS
1.3.3 | Milestone: Project Proposal Approval | Approval of Project plan/ proposal | 5 Days | 2017-04-09 | 1.3.2 FS | Approved Project Topic Proposal
2 | Analysis |  | 75 Days | 09/25/2017
2.1.1 | Finalize Revisions | Editing of document | 10 Days | 09/25/2017
2.1.2 | Started Drafting other documents (Vision and scope, SRS, etc.) | Start additional requirements | 10 Days | 2017-02-10
2.2.1 | Create System Diagrams | Design System | 40 Days | 2017-09-10 |  | Create Diagrams
2.2.2 | Review + Present Diagrams | Checking of Design | 10 Days | 2017-11-12 | 2.2.1 FS
2.2.3 | Update Diagarms | Revisions | 5 Days | 2018-03-01 | 2.2.2 FS | Revise Diagrams
3 | Project Development |  | 50 Days | 01/18/2018 |  | Develop Mobile + Web Application
3.1.1 | Develop Login + Menu | Development of Mobile Application | 5 Days | 01/18/2018
3.1.2 | Develop Locate Bus + Bus Stop Feature Develop Locate Bus + Bus Stop Feature Login + Menu | Development of Mobile Application | 10 Days | 01/25/2018
3.1.3 | Map Feature | Development of Mobile Application | 5 Days | 2018-08-02
3.1.4 | Reservation System | Development of Mobile Application | 20 Days | 02/15/2018
3.1.5 | Congestion Forecasts | Development of Mobile Application | 10 Days | 03/15/2018
3.1.6 | User Review Module | Development of Mobile Application | 5 Days | 03/29/2018
3.2.1 | Develop Login + Menu for Administrator | Development of Web Application | 5 Days | 2018-08-02
3.2.2 | Develop storage for congestion status and News reports | Development of Web Application | 15 Days | 02/15/2018
3.2.3 | Develop other Feature + Front End | Development of Web Application | 15 Days | 2018-02-03
4 | Implementation |  | 10 Days | 2018-05-04
4.1.1 | Develop Test Report | Test Report | 1 Day | 2018-05-04
4.1.2 | Test System | Test Case | 7 Days | 2018-09-04
4.1.3 | Implement System | System Deployment | 2 Days | 04/18/2018 |  | System Deployment
5 | Closure |  | 6 Days | 04/19/2018
5.1.1 | Finalize Project Documentation | Finalize final document | 3 Days | 04/19/2018
5.1.2 | Complete Project Requirements | Finish other major requirements | 2 Days | 04/23/2018 |  | Finish Requirements
5.1.3 | Assess group performance | Group Assessment | 1 Day | 04/25/2018 |  | Assess group performance